## Implementation Plan
Phase | Task ID | Task | Description | Owner | Priority | Status | Start Date | End Date | Dependency | Deliverable | Acceptance Criteria
1. Discovery | 1.1 | Complete branch infrastructure audit | Record existing servers, firmware, network, storage, power, backup and AD details. | Infrastructure Engineer | High | Not Started | 2026-05-01 | 2026-05-03 | None | Completed branch audit sheet | Audit completed and reviewed
1. Discovery | 1.2 | Confirm current VM inventory | Identify DC1, DC2, DHCP1, MGMT1, FILE1 and any branch-specific VMs. | Infrastructure Engineer | High | Not Started | 2026-05-01 | 2026-05-03 | 1.1 | Validated VM list | All VMs documented
1. Discovery | 1.3 | Confirm site readiness | Check rack space, UPS capacity, PDU capacity, cooling and switch ports. | Project Manager | High | Not Started | 2026-05-02 | 2026-05-04 | 1.1 | Site readiness approval | Site approved for upgrade
2. Existing Host Upgrade | 2.1 | Update firmware baseline | Update BIOS, iDRAC, RAID controller, NIC and chipset firmware on HV01 and HV02. | Infrastructure Engineer | High | Not Started | 2026-05-05 | 2026-05-06 | 1.3 | Firmware update record | Both hosts match approved baseline
2. Existing Host Upgrade | 2.2 | Patch Windows Server | Apply approved Windows Server 2022 Datacenter updates through WSUS. | Infrastructure Engineer | High | Not Started | 2026-05-06 | 2026-05-06 | 2.1 | Patch record | No critical updates outstanding
2. Existing Host Upgrade | 2.3 | Validate Hyper-V configuration | Confirm virtual switches, VLANs, host management and VM networking. | Infrastructure Engineer | High | Not Started | 2026-05-07 | 2026-05-07 | 2.2 | Hyper-V validation record | Hyper-V configuration healthy
2. Existing Host Upgrade | 2.4 | Validate Failover Clustering feature | Install or confirm Failover Clustering feature on existing hosts. | Infrastructure Engineer | Medium | Not Started | 2026-05-07 | 2026-05-07 | 2.2 | Cluster feature confirmation | Feature available on both hosts
3. Third Server Installation | 3.1 | Rack and cable HV03 | Install Dell PowerEdge R670, connect power rails, iDRAC, management, storage and VM trunk links. | Infrastructure Engineer | High | Not Started | 2026-05-08 | 2026-05-08 | 1.3 | Cabling record | Server powered and cabled correctly
3. Third Server Installation | 3.2 | Install Windows Server 2022 Datacenter | Install OS on RAID 1 boot storage and apply baseline configuration. | Infrastructure Engineer | High | Not Started | 2026-05-08 | 2026-05-09 | 3.1 | Installed server | HV03 boots and is reachable
3. Third Server Installation | 3.3 | Install roles and features | Install Hyper-V and Failover Clustering on HV03. | Infrastructure Engineer | High | Not Started | 2026-05-09 | 2026-05-09 | 3.2 | Configured server role | Required roles installed
3. Third Server Installation | 3.4 | Join HV03 to domain | Join HV03 to corp.electric-petrol.ie and place in correct OU. | Infrastructure Engineer | High | Not Started | 2026-05-09 | 2026-05-09 | 3.2 | Domain-joined host | Domain login works
4. Shared Storage | 4.1 | Configure storage VLAN | Validate VLAN 9 and storage switch connectivity for all three hosts. | Network Engineer | High | Not Started | 2026-05-10 | 2026-05-10 | 3.4 | Storage VLAN confirmation | All hosts reach storage network
4. Shared Storage | 4.2 | Configure shared storage | Present shared storage to HV01, HV02 and HV03. | Storage Engineer | High | Not Started | 2026-05-10 | 2026-05-11 | 4.1 | Shared storage target | All hosts can see shared storage
4. Shared Storage | 4.3 | Configure Cluster Shared Volumes | Configure CSVs for Hyper-V virtual machine storage. | Infrastructure Engineer | High | Not Started | 2026-05-11 | 2026-05-11 | 4.2 | CSV configuration | CSV visible to all cluster nodes
5. Cluster Build | 5.1 | Run Cluster Validation Wizard | Run Microsoft cluster validation before creating or expanding cluster. | Infrastructure Engineer | High | Not Started | 2026-05-12 | 2026-05-12 | 4.3 | Validation report | Cluster validation passes
5. Cluster Build | 5.2 | Create three-node cluster | Add HV01, HV02 and HV03 to the Hyper-V Failover Cluster. | Infrastructure Engineer | High | Not Started | 2026-05-12 | 2026-05-12 | 5.1 | Three-node cluster | All nodes online
5. Cluster Build | 5.3 | Configure Live Migration | Configure Live Migration network, authentication and host settings. | Infrastructure Engineer | High | Not Started | 2026-05-13 | 2026-05-13 | 5.2 | Live Migration config | Test VM migrates successfully
5. Cluster Build | 5.4 | Make VMs highly available | Move branch VMs to CSV and configure as highly available workloads. | Infrastructure Engineer | High | Not Started | 2026-05-13 | 2026-05-14 | 5.2 | Highly available VMs | Critical VMs visible in Failover Cluster Manager
6. AAA and AD | 6.1 | Create AD admin groups | Create GG-HyperV-Admins, GG-Cluster-Admins, GG-Storage-Admins and support groups. | AD Administrator | High | Not Started | 2026-05-14 | 2026-05-14 | 3.4 | AD groups created | Groups visible in AD
6. AAA and AD | 6.2 | Apply Group Policy | Apply server baseline, Hyper-V host policy, audit policy and WSUS policy. | AD Administrator | High | Not Started | 2026-05-15 | 2026-05-15 | 6.1 | GPOs linked | Policies apply correctly
6. AAA and AD | 6.3 | Configure RADIUS/NPS | Integrate network device administration with AD groups where required. | Network Engineer | Medium | Not Started | 2026-05-15 | 2026-05-16 | 6.1 | NPS configuration | Test admin authentication works
7. Monitoring and Backup | 7.1 | Add hosts and cluster to monitoring | Monitor host health, cluster health, storage, NICs, iDRAC and UPS. | Monitoring Engineer | High | Not Started | 2026-05-16 | 2026-05-16 | 5.2 | Monitoring dashboard | Test alert received
7. Monitoring and Backup | 7.2 | Update backup jobs | Update backup software to protect VMs on shared storage. | Backup Administrator | High | Not Started | 2026-05-16 | 2026-05-17 | 5.4 | Updated backup jobs | Backup completes successfully
7. Monitoring and Backup | 7.3 | Perform test restore | Restore a test VM to confirm backup integrity. | Backup Administrator | High | Not Started | 2026-05-17 | 2026-05-17 | 7.2 | Restore evidence | VM restores and boots
8. Pilot Acceptance | 8.1 | Test host failure | Simulate one host failure and confirm critical VMs restart on surviving hosts. | Infrastructure Engineer | High | Not Started | 2026-05-18 | 2026-05-18 | 5.4 | Failover test result | Single host failure tolerated
8. Pilot Acceptance | 8.2 | Complete acceptance sign-off | Review cluster, backup, monitoring, AD and documentation with operations team. | Project Manager | High | Not Started | 2026-05-19 | 2026-05-19 | 8.1 | Signed acceptance | Pilot branch accepted
9. National Rollout | 9.1 | Update rollout standard | Incorporate pilot lessons into final build standard. | Project Manager | High | Not Started | 2026-05-20 | 2026-05-20 | 8.2 | Final rollout standard | Standard approved
9. National Rollout | 9.2 | Roll out branches in batches | Upgrade 3 to 5 branches per batch using approved standard. | Project Team | High | Not Started | 2026-05-21 | 2026-07-31 | 9.1 | Completed branch batches | All branches upgraded
10. Handover | 10.1 | Complete operational handover | Provide hostnames, IPs, VLANs, cluster details, storage details, backups and support contracts. | Project Manager | High | Not Started | 2026-08-01 | 2026-08-05 | 9.2 | Handover pack | Operations team accepts support

## Summary
Electric-Petrol.ie A3 Management Implementation Plan
Workbook Purpose | Track the upgrade from two Hyper-V hosts to a three-node clustered branch design.
Total Tasks | 29
Complete | 0
In Progress | 0
Blocked | 0
Not Started | 29
Completion % | 0%

## Lists
Status | Priority | Owner
Not Started | High | Project Manager
In Progress | Medium | Infrastructure Engineer
Blocked | Low | Network Engineer
Complete |  | Storage Engineer
AD Administrator
Backup Administrator
Monitoring Engineer
Project Team